## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Andrew | Blake | Danny | Jacob | Lila | Renny | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | By Task |  |  | Scale of 0-5; Fill your row.
Preliminary & | [16 empty] | Andrew | Blake | Danny | Jacob | Lila | Renny | Average
Parallel Tasks | Architecture |  |  |  |  | 0 |  | 0 | [7 empty] | Andrew |  | 5 | 5 | 5 | 5 | 5 | 2.6667
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Blake | 2 | 5 | 4 | 4 | 0 | 4 | 4.1667
| Requirements |  |  |  |  | 5.5 |  | 5.5 | [6 empty] | 0 | Danny | 5 | 5 | 5 | 5 | 5 | 5 | 4
|  | Meet with mentors | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 1.5 |  | 1.5 |  | 2 | 1 | 1 | 1 |  | 1 | 6 | Jacob | 4 | 5 | 5 | 0 | 4 | 4 | 3.1667
|  | Met to discuss requirements | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 3 |  | 3 |  | 2 | 1 | 2 | 2 |  | 2 | 9 | Lila | [6 empty] | 3.1667
|  | Email mentors | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 1 |  | 1 |  | 1 | 2 | 1 | 1 |  | 1 | 6 | Renny | 5 | 5 | 5 | 5 | 5 | 5 | 3.8333
| Documentation |  |  |  |  | 3 |  | 3 | [6 empty] | 0
|  | Project Charter | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 2 |  | 2 |  | 0 | 3 | 2 | 2 |  | 2 | 9
|  | Set up github | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 1 |  | 1 |  | 0.5 | 3 | 1 | 1 |  | 0.5 | 6
Coding
Iteration 1: | Design |  |  |  |  | 31 |  | 31 | [6 empty] | 0
|  | Design Discussion | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 20 |  | 20 |  | 3 | 3 | 3 | 3 |  | 3 | 15
|  | Determining framework | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 10 |  | 10 |  | 3 | 3 | 3 | 3 |  | 3 | 15
|  | Meet with Mentors for project presentation | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 1 |  | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 5
| Development |  |  |  |  | 2.5 |  | 2.5
|  | Create and upload website | Developer | Danny | 2.5 |  | 2.5 |  | 0 | 0 | 2.5 | 0 |  | 0 | 2.5
|  | Set up database | Developer | Lila |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0
| Analysis |  |  |  |  | 20 |  | 20 | [6 empty] | 0
|  | Filled out project design documents | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 20 |  | 20 |  | 3 | 3 | 3 | 3 |  | 3 | 15
Iteration 2: | Design |  |  |  |  | 5 |  | 5 | [6 empty] | 0
|  | Investigating Databases | All | Blake | 3 |  | 3 |  | 0 | 3 | 0 | 0 | 0 | 0
|  | Transaction page UI Design | All | All | 2 |  | 2 |  | 0 | 2 | 2 | 2 | 2 | 2
| Development |  |  |  |  | 21.5 |  | 12 | [6 empty] | 0
|  | Create the Login Page | Developer | Renny | 6.5 | 5 | 3 |  | 0 | 0 | 0 | 0 | 0 | 5
|  | Create Transaction Summary Page | Developer | Jacob | 10 |  | 4 |  | 0 | 4 | 0 | 4 | 0 | 0
|  | Link Firebase to our react app | Developer | Blake | 5 |  | 5 |  | 0 | 5 | 0 | 0 | 0 | 0
| Analysis |  |  |  |  | 0 |  | 0 | [6 empty] | 0
Iteration 3: | Design |  |  |  |  | 4 |  | 0 | [6 empty] | 0
|  | Comeplete Architecture document | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 4
| Development |  |  |  |  | 10 |  | 0 | [6 empty] | 0
|  | Finish transaction page | Developer | Blake, Jacob, Danny | 4
|  | Create notification page | Developer | Andrewm, Blake | 6
| Analysis |  |  |  |  | 0 |  | 0 | [6 empty] | 0
Total |  |  |  |  | 102.5 | 107.5 | 94.5 | 79 | 15.5 | 34 | 21.5 |  |  | 23.5 | 94.5