## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Andrew | Blake | Danny | Jacob | Lila | Renny | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 0 |  | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements |  |  |  |  | 5.5 |  | 5.5 | [6 empty] | 0
|  | Meet with mentors | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 1.5 |  | 1.5 |  | 2 | 1 | 1 | 1 |  |  | 5
|  | Met to discuss requirements | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 3 |  | 3 |  | 2 | 1 | 2 | 2 |  |  | 7
|  | Email mentors | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 1 |  | 1 |  | 1 | 2 | 1 | 1 |  |  | 5
| Documentation |  |  |  |  | 3 |  | 3 | [6 empty] | 0
|  | Project Charter | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 2 |  | 2 |  | 0 | 3 | 2 | 2 |  |  | 7
|  | Set up github | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 1 |  | 1 |  | 0.5 | 3 | 1 | 1 |  |  | 5.5
Coding
Iteration 1: | Design |  |  |  |  | 31 |  | 31 | [6 empty] | 0
|  | Design Discussion | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 20 |  | 20 |  |  | 3 | 3 | 3 |  |  | 9
|  | Determining framework | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 10 |  | 10 |  |  | 3 | 3 | 3 |  |  | 9
|  | Meet with Mentors for project presentation | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 1 |  | 1 |  |  | 1 | 1 | 1 |  |  | 3
| Development |  |  |  |  | 2.5 |  | 2.5
|  | Create and upload website | Developer | Danny | 2.5 |  | 2.5 |  |  | 0 | 2.5 | 0 |  |  | 2.5
|  | Set up database | Developer | Lila | [5 empty] | 0 |  | 0 |  |  | 0
| Analysis |  |  |  |  | 20 |  | 20 | [6 empty] | 0
|  | Filled out project design documents | All | Andrew, Blake, Danny, Jacob, Lila, Renny | 20 |  | 20 |  |  | 3 | 3 | 3 |  |  | 9
Iteration 2: | Design |  |  |  |  | 0 |  | 0 | [6 empty] | 0
| Development |  |  |  |  | 0 |  | 0 | [6 empty] | 0
| Analysis |  |  |  |  | 0 |  | 0 | [6 empty] | 0
Iteration 3: | Design |  |  |  |  | 0 |  | 0 | [6 empty] | 0
| Development |  |  |  |  | 0 |  | 0 | [6 empty] | 0
| Analysis |  |  |  |  | 0 |  | 0 | [6 empty] | 0
Total |  |  |  |  | 62 | 62 | 45 | 62 | 5.5 | 20 | 19.5 |  |  | 0 | 45